## Q4 2025
Division: | Nuclear Sciences | Risk Analysis Q4 2025 |  | Critical risks
1 | Critical risks
Risks with high exposure, overdue action, and a departmental escalation
| Risk Id | Department | Area | Sub-area | Risk exposure | Action status | Action Owner
| R00088 | Nuclear Applications | Procure-to-Pay (P2P) cycle | Sourcing | High | Ongoing (overdue) | Sandra A
| R00127 | Finance | Financial management & reporting | Advances | High | Ongoing (overdue) | Martina N
2 | Risks to monitor
Risks with high exposure, overdue action, but no departmental escalation
| Risk Id | Department | Area | Sub-area | Risk exposure | Action status | Action Owner
| R00087 | Nuclear Applications | Procure-to-Pay (P2P) cycle | Sourcing | High | Ongoing (overdue) | Sandra A
| R00090 | Nuclear Applications | Procure-to-Pay (P2P) cycle | Sourcing | High | Ongoing (overdue) | Chris T