## Slide 1
Division of Human Health – Development projects IT portfolio - Human Health Revamp Q1 2026 Status update
Data as of April 10, 2026
Product | Q1 2026 Planned Budget (USD) | Q1 2026 Actual Budget Utilization (USD) | Percentage variance (%) | RAG Status
Reports | 22,500 | 9,440 | -58.0 | Green
Mobile App | 30,000 | 30,288 | 1.0 | Amber
Integration API | 7,500 | 3,820 | -49.1 | Green
Maintenance | 20,000 | 39,285 | 96.4 | Red
RAG Status: 15% or above overbudget – Red, less than 15% overbudget – Amber, on or underbudget - Green
Portfolio Budget Utilization Status
Q1 2026
Planned Budget: USD 80,000
Actual Budget Utilization: USD 82,833
3.5% Overbudget
Percentage variation (planned vs actuals)
RAG Status: Amber
Key insights
Activities that contributed to positive variation (overbudget):
Maintenance (Product: Maintenance)
Design (Product: Mobile App)
Implementation (Product: Mobile App)
Testing (Product: Mobile App)
Flagged vendors with percentage variation in planned budget and actual budget utilization:
Vendor STS – Freeze PO (118.3%)
Vendor RTA – Needs escalation (74.6%)
Chart: Planned vs Actual budget utilization by Product, Q1 2026
| Reports | Mobile App | Integration API | Maintenance
Q1 Planned Budget (USD) | 22500 | 30000 | 7500 | 20000
Q1 Actual Budget Utilization - Internal team (USD) | 9440 | 30287.5 | 3820
Q1 Actual Budget Utilization - Vendors (USD) | 39285